## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  | 1 | Foundations and Prerequistes for doing the project |  |  |  | 3- Completed
|  | 2 | Project Understanding, Setup, project achitecture and Google sheet Integration |  |  |  | 3- Completed
|  | 3 | Social Media Integration, Content Creation, Optimization |  |  |  | 3- Completed
|  | 4 | Sentiment Analysis, Slack Integration and deployment |  |  |  | 3- Completed
Note on F1: ====== ID#AAABs4-wLUs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Difficulty understanding complete project requirements and end-to-end workflow | Conducted mentor explanation session + reviewed documentation
Sprint 1 | Day 5 | Confusion in Python fundamentals while practicing | Revisited topics and practiced additional programs
Sprint 2 | Day 8 | Challenge in correctly mapping Google Sheets with the project | Re-checked credentials & used proper API token mapping with mentor assistance
Sprint 2 | Day 10 | Difficulty understanding OOPS + Module imports for project structure | Watched tutorials + mentor support + hands-on practice
Sprint 2 | Day 13 | Environment setup issues (Virtual environment + installation errors) | Re-installed dependencies & verified installation using mentor guidance
Sprint 3 | Day 16 | Twitter / social media API integration issues (Auth failure) | Updated keys & corrected API endpoint calls
Sprint 3 | Day 18 | Groq API credential errors | Requested new API key and corrected environment variables
Sprint 3 | Day 20 | Difficulty generating multiple content variations automatically | Implemented fallback mechanism + prompt improvements
Sprint 4 | Day 24 | Sentiment analysis results inconsistent → classification confusion | Validated results using additional datasets & mentor guidance
Sprint 4 | Day 26 | Slack message push not working initially | Updated correct webhook and verified connection
Sprint 4 | Day 28 | Streamlit deployment blank page | Debugged layout errors & re-ran server + fixed imports
Sprint 4 | Day 29 | A/B Testing “recommended” key error → app crash | Fixed code logic + added default return values
Sprint 4 | Day 30 | Google Sheets logs not visible due to connectivity timeout | Added retry handling + verified internet permissions

## Sprint Backlog
L
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 |  | Foundations and Prerequistes for doing the project | 23rd Sep | 7th Oct | Gaddam Meghana | Learned Core Python Concepts | Done |  | Introduction | Installed Python and Jupyter Notebook Environment | History and Introduction of Python | Learnt naming conventions, variables,.. | Understood the Concept and Usage of Data Types in Python | practiced program that i had learned at previous class | Practiced Example programmes on all the topics which are covered | Gained understanding of string handling in Python | Practiced Python string concepts | Practiced Python programs learned so far | Practiced using built-in string functions | practiced functions | Revised all topics through example-based Python programs | Learnt functions concept
2 |  | Project Understanding, Setup, project achitecture and Google sheet Integration | 8th oct | 22nd oct | Gaddam Meghana | Implementation Setup & Google Sheet Mapping | Done |  | Understanding OOPS concept | Understood Packages, Modules, Importing | Learned NLP concept | Learned about NLTK,Spacy | learned about SpaCy | understood about project | Interaction session on project | Understood how to Install Virtual Environment | Learned about Hugging Face Transformers | Project understanding interactive session | Revised Hugging Face Transformer | Revised Python concepts | Practice Transformer and Python Concept | API integration with google sheets
3 |  | Social Media Integration, Content Creation, Optimization | 23rd Oct | 6th Nov | Gaddam Meghana | Implemented social media API integration and applied various content generation approaches | Done |  | Explore how to integarte APIs with twitter | Worked on API integration of twitter | Gathered API credentials for Instagram and Facebook. | Worked on Linkedin API integration | Interactive session with sir | Practiced API integration code implementation | Understood fundamentals of mock data generation | Understood how to create content and use Groq API | Hands-on practice with gsheet_connector | Introduction to LLM | Revised LLM | Interactive Session | Understood about How to generate different versions of Content | Practiced different content generations
4 |  | Sentiment Analysis, Slack Integration and deployment | 6th Nov | 20th Nov | Gaddam Meghana | Sentiment Analysis, Slack Integration and deployment | Done |  | Gained knowledge about application programing interface and there stages | Understood about API | Revisited API concepts for improved clarity and confidence | Worked on Assignment | Interactive session | learned how to optimize content | understood sentiment analysis | Studied slack integration | Learnt about A/B Testing | Revisied the concept of A/B testing | Practice on Content optimization and sentiment Analysis | Understood about Project Workflow | Presentation preparation and discussion | Mock presentation
Note on D2: ====== ID#AAABs4-wLUI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABs4-wLVM Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABs4-wLUM Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABs4-wLUY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABs4-wLU8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABs4-wLUw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABs4-wLU0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABs4-wLVA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABs4-wLUU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABs4-wLUc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABs4-wLUg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABs4-wLUk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABs4-wLVE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABs4-wLUo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABs4-wLVI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABs4-wLUQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABs4-wLU4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-09-25 | 2025-10-07 | Gaddam Meghana | Practicing Python fundamentals with coding tasks | Just reading theory without hands-on | Revision after each concept | Completed Python basics (variables, strings, loops, functions) and built small practice programs
2 | Sprint 2 | 2025-10-08 | 2025-10-22 | Gaddam Meghana | Setting up APIs and the project environment properly | Delaying environment setup and integrations | Clarifying doubts with mentor | Integrated Google Sheets with API credentials and set up the project structure successfully
3 | Sprint 3 | 2025-10-23 | 2025-11-06 | Gaddam Meghana | Working on social media integration and content generation | Trying to test everything manually first | Improving content generation features with Groq/Gemini | Successfully implemented Twitter API posting, created content variations, and tested automation for posting
4 | Sprint 4 | 2025-11-07 | 2025-11-24 | Gaddam Meghana | Performing Sentiment Analysis, A/B Testing, and Slack notifications | Ignoring minor backend errors during testing | Improve UI and execution flow with Streamlit | Integrated sentiment engine, A/B test comparison, Slack alerts & executed full pipeline end-to-end